## README
Last Update | 2018-11-28
Author | Andrew Cruz, Neesha Bhardwaj, Jonathan Kaneshiro, Chianh Wu
Email | acruz029@ucr.edu, nbhar003@ucr.edu, jkane002@ucr.edu, cwu048@ucr.edu
Description | This is a SCRUM template designed for W9 project managment in CS180. Team: Eat,Sleep,Code. Section 22. Neesha Bhardwaj, Andrew Cruz, Jonathan Kaneshiro, Chianh Wu
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Parking List View | As a student, I want to see which parking lots have spaces available and how many each has. | 4 | 1
2 | Push Notifications | As a user, I want to get notifications that alert me when a parking lot on campus is full so I know to avoid trying to park there. | 5 | 1
3 | Directions and locations | As a user, I want to see the fastest directions to the parking lot so that I can be more time efficient. | 6 | 2
4 | Permit information | As a user, I want to see which parking lot accepts my permits so that I do not get a citation. | 2 | 3
5 | Schedule Input | As a user, I want to be able to find parking locations based on my class schedule and find the closest parking lot and/or space to that building. | 6 | 2
6 | Parking trends | As a user, I want to know the busiest times and most available times of when to park | 2 | 5
7 | Info page (TAPS) | As a user, I want to check information regarding TAPS. | 3 | 4
8 | Menu | As a user, I want to choose which options to select when first opening the app so I can choose which user interface is better and easier to understand. | 4 | 1
9 | Map View | As a user, I want to see a map view of the campus and parking lots given the permit that I have. | 5 | 1
10 | Save my parked location | As a user, I want to be able to save my parked location so that I can remember where I parked once I get out of class. | 6 | 3
| Total |  | 43 | Note: Priority is 1-5 1 highest 5 lowest

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Menu View (Sprint 1) Jonathan/ Neesha
Task 2: Schedule Input Form (Manual) (Sprint 1) Andrew
Task 3: Parking view backend (Sprint 1) Chianh
Task 4: Map View (Sprint 2) Andrew
Task 5: Info page (TAPS) (Sprint 2) Neesha
Task 6: Store Schedule Info (Sprint 2) Andrew
Task 7: Parsing parking lots (Sprint 2) Chianh
Task 8: Splash Screen (Sprint 2) Jonathan
Task 9: Overall UI (Sprint 3) Jonathan
Task 10: Remove Classes from Schedule (Sprint 2) Andrew
Task 11: Save parked location (Sprint 3) Chianh
Task 12: Push notifications (Sprint 3) Neesha
Task 13: Parking trends (Sprint 3) Jonathan

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 0 | 0 | 0 | 43 | 43
1 | 14 | 14 | 14 | 29 | 28.6667
2 | 12 | 12 | 26 | 17 | 14.3333
3 | 17 | 17 | 43 | 0 | 0

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Jonathan | Task 1: Menu View, Task 2: Schedule Input, Task 3: Parking Activity
2 | Andrew | Task 4: Parse Parking, Task 5:Map View, Task 6: Taps Info Page
3 | Neesha | Task 7: Save parked location, Task 8: Push notifications, Task 9: Parking trends,